## Slide 1
Radiological Health Program
Modernization Initiative
Executive Status Report · FY26 · June 12, 2026
⬤ Overall Status: YELLOW
Maryland Department of the Environment (MDE) · PCA: 79103 · Fund: Radiation Control Fund
Prepared for Executive Review · July 10, 2026
☢

## Slide 2
Project Overview
Overall: YELLOW
INITIATIVE
The Radiological Health Program (RHP) is launching a strategic modernization initiative to transition its permitting and licensing application pipeline from legacy, manual workflows to a centralized online portal and electronic payment module.
HEALTH STATUS INDICATORS
G
Scope
G
Schedule
G
Cost
G
Risk
R
Quality
Y
Resources
⚠ WHY YELLOW?
Environment and resource changes have been identified during the reporting period. These changes are not expected to impact overall project delivery. The team is actively hiring a Tech Lead to prevent future environmental and build blockers, as key agency technical resources are engaged in other internal initiatives.
Reporting Period: FY26 · Jun 12, 2026

## Slide 3
Sprint Schedule & Delivery Milestones
Sprint 2: IN PROGRESS
Sprint 1
Jun 17 – Jun 30, 2026
Group 3–9: PDF Portal Submissions & Electronic Payments enabled
100%
Complete
Sprint 2
Jul 1 – Jul 14, 2026
Group 3–9: Enable Notifications for customers & RHP Team Inbox
64%
In Progress
Sprint 3
Jul 15 – Jul 28, 2026
Group 3–9: Provide option to download RHP permits
0%
Not Started
Sprint 4
Jul 29 – Aug 11, 2026
Group 3–9: Reject & update status (CRM) for RHP permits
0%
Not Started
Sprint 5
TBD
Group 1–2: Configuration and setup
0%
Not Started
Sprint 6
TBD
Group 3–9: Web Forms Development
0%
Not Started
Near = within 2 sprints · Next = planned future sprints

## Slide 4
Financial Summary
Cost Status: GREEN
Total Approved
$6.0M
FY25–FY26 Combined
Total Forecast
$3.70M
FY25–FY28 All Years
Total Actual
$1.45M
FY25 + FY26 Spent
Remaining
$1.55M
Balance / Variance
Fiscal Year
Approved
Forecast
Actual
Balance
Fund Source
FY-25
$1,000,000
$500,000
$275,086
$724,914
Radiation Control (SF)
FY-26
$2,000,000
$1,200,000
$1,177,504
$822,496
Radiation Control (SF)
FY-27
$3,000,000
$1,468,511
—
$0
Special
FY-28
—
$535,591
—
$0
Special
TOTAL
$6,000,000
$3,704,102
$1,452,590
$1,547,410
—
BUDGET UTILIZATION (ACTUAL vs APPROVED)
FY-25
27.5%
FY-26
58.9%
FY-27
0.0%
PCA: 79103 · Object Code: Radiation Control Fund

## Slide 5
MVP Capabilities — Groups 3 through 9
📄
Portal Submissions
PDF application submissions through the ESC Portal for Groups 3–9.
💳
Electronic Payments
Credit/debit card and E-check capabilities to immediately resolve clearing delays.
🔔
Notifications
One-time email confirmations for end-users upon application and payment submission.
📥
RHP Team Inbox
Automated notifications delivered to the MDE Business User (RHP Team) inbox.
📁
Document Management
Secure view, download of applications and supporting documents — individual files or ZIP.
🔐
IAM Authentication
MDE Business User authentication via Identity and Access Management (IAM) protocols.
Groups 1–2 configuration and setup planned in Sprint 5

## Slide 6
Risks, Impediments & Action Items
ACTIVE RISKS & IMPEDIMENTS
HIGH
Environment & Build Issues
Encountered environment and build issues impacting iterative delivery. Development and validation processes are established and being monitored. Mitigation: Hiring a Tech Lead to address future environmental/build blockers.
RESPONSE STRATEGY
Mitigate
MEDIUM
Workflow Finalization
Non-ETS workflow approach requires finalization: future status tracking, Third-Party access (Inspectors), Liability Checks, and invoice payment features. DoIT & MDE teams reviewing enterprise solutions.
RESPONSE STRATEGY
Transfer
MEDIUM
Registration Number Automation
Program must decide on folder naming convention and whether the system auto-generates sequence numbers as part of modernization, or continues the current manual process. Awaiting program decision.
RESPONSE STRATEGY
Mitigate
ACTION ITEMS
MVP Time Savings
Collaborate with program team to generate high-level estimates of days saved per MVP deliverable (80/20 rule).
Liability Check
Remain closely coordinated with Emil, Paul, and the DoIT team while awaiting update from State Data Officer.
User Testing
Align with Paul to ensure user testing is seamlessly integrated into development cycles.
Risk Strategy: Mitigate = internal action · Transfer = escalate / partner

## Slide 7
Successes & Key Progress — Reporting Period
✅
MVP Release Development
The team is actively working on the MVP release supporting New Applications for Groups 3 through 9. Re-certification and Renewal workflows are under review pending Liability Check clarification (Certificate of Good Standing — new system does not require Tax ID or SSN).
⚙️
ESC Page Validations & Verification
The RHP Team is developing the RHP Configuration Template to govern ESC Portal page validations, ensuring data integrity and compliance across all application submissions.
🔐
Authentication & Database Restructuring
Work has commenced on MDE Business User authentication using Identity and Access Management (IAM) protocols, alongside the necessary restructuring of legacy RHP applications and database tables to support modern workflows.
Sprint 1 completed successfully · Sprint 2 currently in progress (Jul 1–14, 2026)

## Slide 8
Executive Summary & Next Steps
Overall
YELLOW
Schedule
ON TRACK
Cost
ON TRACK
Delivery
MVP Q3
KEY TAKEAWAYS
On Budget
Actual spend of $1.45M is tracking below forecast. Remaining balance of $1.55M provides healthy fiscal buffer.
Delivery On Track
Sprint 1 completed. Sprint 2 in progress. Core MVP capabilities on schedule for Groups 3–9.
Quality Attention Needed
Build/environment issues were encountered in Sprint 1. Tech Lead hiring in progress to prevent recurrence.
Decisions Pending
Workflow finalization and registration number automation require program decisions to maintain velocity.
IMMEDIATE NEXT STEPS
Complete Sprint 2
Jul 1–14, 2026
Enable customer notifications & RHP Team inbox
Finalize Workflow
Ongoing
Resolve non-ETS workflow with DoIT & MDE teams
State Data Officer Input
Awaiting
Liability Check decision needed from Emil/Paul/DoIT
Hire Tech Lead
Active Recruiting
Address build/environment blockers proactively
User Testing Alignment
Sprint 2–3
Coordinate with Paul to integrate testing into dev cycle
RHP Modernization Initiative · MDE · Prepared for Executive Review · July 10, 2026